## Slide 1
Solaroo RE CRM
Sales-to-Project Lifecycle Flowcharts
Account · Site · Opportunity · Proposal · Contract · Project · Commissioning · O&M
Pekat Teknologi Sdn Bhd · Internal CRM platform · v1

## Slide 2
End-to-End Lifecycle — One-Page Master Flow
From first contact to operating asset. Each stage is a CRM module.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Account & Site
Customer + location record created
Contact
Decision-makers linked to account
Opportunity
Deal record + stage history
Proposal (versions)
Frozen assumption set per version
Contract awarded
Signed scope + milestones
Project (auto-created)
PM assigned at WON. Gates open.
Procurement + Site Exec
RFQs · POs · Deliveries · Build
Commissioning + Handover
Tests passed. Assets registered.
O&M (operating)
Tickets, maintenance, warranty
Cross-cutting — applied to every stage:
Activity Timeline
Every call/email/visit logged
Next-Action Discipline
One open action per opp
Health Indicator
Healthy / At Risk / Stale / Overdue
Notifications
Bell alerts + daily digest
Audit Log
Every status change recorded
Role-based Visibility
Margin/CAPEX restricted
Primary owners by stage:
Sales Engineer
Sales Engineer
Sales Engineer / Manager
Sales Eng + Design Lead
Sales Manager + Director
PMO Manager → PM
Procurement + Site Sup.
Commissioning Eng.
O&M Engineer

## Slide 3
1. Lead Capture & Qualification
How a new enquiry becomes a qualified opportunity in the CRM.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Lead sources
Inbound web / call
Referral
Trade show / expo
Existing account
Sales Engineer captures lead in CRM
Account (if new)
company / industry
Site (if new)
geo, capacity, grid
Contact(s)
name, role, email
Opportunity created · stage = QUALIFICATION
Qualified? (budget · authority · need · timeline)
Stage → NEEDS_ASSESSMENT
Yes
Stage → LOST · reason recorded
No
Discipline applied immediately
• Set Owner = capturing user
• Log inbound activity (CALL / EMAIL)
• Set first Next Action: SITE_SURVEY or FOLLOW_UP
• Set Due Date (≤ 7 days)
• Save → opportunity becomes 'Healthy'
Notifications wired:
• Overdue next action (daily)
• No activity in 14 / 30 days
• Proposal awaiting follow-up (3d)

## Slide 4
2. Opportunity Stage Flow
Linear stage progression. Stage jumps are blocked. Every transition is audited.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
QUALIFICATION
NEEDS_ASSESSMENT
TECHNICAL_DESIGN
BUDGETARY_PROPOSAL
FIRM_PROPOSAL
NEGOTIATION
CLOSING
WON
LOST · reason required
any stage → LOST
What the system enforces at every stage:
Activity logging
Sales engineer logs call / email / visit / WhatsApp / proposal follow-up
Next action set
Type · owner · due date. Empty slot ⇒ At Risk flag
Health calc
Healthy · At Risk (>14d silent / no action) · Stale (>30d) · Overdue (action past due)
Notifications
Bell alerts to owner + sales manager. Daily digest at 30-min tick
Audit
Every stage change, every field touch, recorded in audit log

## Slide 5
3. Proposal Lifecycle (versions & approval)
Each proposal version freezes its assumption set. Approved versions are immutable.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Sales Engineer
Design Lead
Director / Sales Mgr (Approver)
Customer
Draft v1 + assumptions
Revise v2 if rejected
Issue v_n to customer
Tech sign-off on BoQ / SLD
Approve or reject
Accept / request revision
reject → new version
revision requested
Rules: each version freezes its assumption set · approved versions are immutable · supersession requires a new version · all decisions audited · margin/CAPEX visible to Director + Sales Manager only.

## Slide 6
4. Award & Handover (Opp WON → Contract → Project)
Marking an opportunity WON triggers automatic contract + project creation.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Opportunity → WON
Contract record auto-created
Status = AWARDED Value + scope from final proposal
Project record auto-created
Code · PM assigned Gates open · RAG=Green
Milestones & invoicing schedule
Per contract terms (advance, mob, comm.)
Handover packet
Notification to PM + PMO Manager
Project gates open in sequence (PMO Manager + PM approve closure):
G1 Kickoff
G2 Design
G3 Procurement
G4 Mobilisation
G5 Construction
G6 Commissioning
G7 Handover
G8 Closeout
Triggered notifications:
contract_awarded
Director · Sales Mgr · PM · Finance
contract_handover_ready
PMO Manager + PM
contract_handover_completed
PM + Director
project_member_added
New team member

## Slide 7
5. Project Execution — Gate, RAG & Blocker Flow
Each gate has structured deliverables. Closure requires approver sign-off.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Single-gate state machine
OPEN
IN_PROGRESS
SUBMITTED FOR REVIEW
Approved?
CLOSED
REJECTED
yes
no
Project-level RAG & blocker flow
GREEN
AMBER
RED
PM updates RAG weekly. AMBER/RED requires currentBlocker + blockerOwner + due date.
PM sets blocker
Assign blockerOwnerId
Notify owner
Owner posts update → PM clears blocker → RAG recalculated
Per-gate deliverables (examples):
G1: Kickoff minutes · scope confirmation · risk register
G2: SLD · BoQ · DBD · permit list
G3: PO list · vendor confirmations · logistics plan
G4: Site readiness checklist · HSE plan · mobilisation log
G5: Daily site reports · photos · punch list
G6: Test sheets · SAT/FAT · commissioning checklist
G7: Handover dossier · asset register · warranty docs
G8: Closeout report · lessons learned · final invoice

## Slide 8
6. Procurement Flow (RFQ → PO → Delivery)
Triggered after Gate 2 (Design) closes. Drives Gate 3 (Procurement) closure.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
BoQ released (from Design)
Vendor list shortlisted
RFQ issued
Quotes received + compared
PO raised (approval req'd)
PO issued to vendor
Goods delivered + GRN
Equipment serial recorded
Value > approval threshold?
Director approves
yes
PM signs off
no
PO status changes notify: project PM · project members · all PROCUREMENT-role users
DRAFT
SUBMITTED
APPROVED
ISSUED
PARTIAL DELIVERED
DELIVERED
CLOSED
CANCELLED
On final delivery: serials captured per item → ready for asset register at commissioning

## Slide 9
7. Commissioning → Asset Register → O&M
Where the project becomes an operating asset under maintenance.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Commissioning
Handover & Asset Register
O&M Operating
Pre-commissioning checks
Functional test sheets
SAT / FAT execution
Punch list cleared
Gate 6 closed (PMO approval)
Asset register populated (serial · warranty start · location)
Customer handover dossier
Customer sign-off captured
Gate 7 closed
Notify Finance for final invoice
Maintenance plan auto-created (per asset class)
Service tickets raised as issues arise
Scheduled maintenance executed
Warranty claims filed if needed
Asset history & uptime tracked
Owners & data flow:
• Commissioning Engineer
Runs all test sheets · marks pass/fail · uploads evidence
• PM + PMO Manager
Approve gate closure · sign off handover packet
• Site Supervisor
Captures serials & install location at GRN time
• O&M Engineer
Owns asset post-handover · all tickets routed here
• Finance/Admin
Triggers final milestone invoice on Gate 7 closure

## Slide 10
8. Cross-Cutting Layers — Notifications · Audit · Role Visibility
Same data, different views. The system enforces who sees what at every stage.
Solaroo RE CRM — Sales-to-Project Lifecycle Flowcharts
Notification triggers (in-app bell + daily digest):
Gate submitted/approved/rejected
Gate approver + PM
Proposal submitted/decision
Sales mgr + Director
Opp WON / LOST
Sales team + Director
Deliverable approved
PM + project members
Blocker assigned
Blocker owner only
PO status changed
PM + PROCUREMENT users
Document approved/rejected
Uploader + doc owner
Project member added
New member + PM
Overdue next action
Action + opp owner
Proposal awaiting follow-up (3d)
Opp owner
Stale opportunity (14d)
Opp owner
Daily digest
Each user (opt-in)
Role visibility (sensitive fields):
Director
Sales Mgr
Sales Eng
PMO Mgr
PM
Design
Procure
Site Sup
O&M Eng
Finance
Margin
✓
✓
✓
CAPEX value
✓
✓
✓
Pipeline value
✓
✓
Opportunity $
✓
✓
✓
✓
Project gate
✓
✓
✓
✓
✓
✓
Asset register
✓
✓
✓
✓
✓
Audit log
✓
✓