Solaroo RE CRM

User Onboarding & System Reference

Pekat Teknologi Sdn Bhd · Internal CRM for Off-grid Solar & BESS Projects

Version 1.0 · April 2026

For questions: see@pekatgroup.com

# Contents

Contents	2

1. System Architecture	4

1.1 Technology Stack	4

1.2 Module Map	4

1.3 Information Flow	4

1.4 Permission Model	4

2. Roles & Responsibilities	6

3. Workflows	8

3.1 Lead → Opportunity	8

3.2 Proposal	8

3.3 Contract & Award→Handover	8

3.4 Milestones & Invoices	9

3.5 Project Execution — Gates 1 to 6	9

3.6 Documents & Revisions	10

3.7 Procurement	10

3.8 Commissioning & O&M	10

3.9 PMO Dashboard	10

3.10 Notifications & Daily Digest	10

3.11 Saved Views	11

3.12 Audit Log	11

4. Worked Example — One Project, End-to-End	12

4.1 Day 1 — Sales Engineer captures the lead	12

4.2 Week 2 — Qualification	12

4.3 Week 4 — Technical Assessment	12

4.4 Week 6 — Proposal v1 issued	12

4.5 Week 9 — Negotiation	12

4.6 Week 12 — WON	13

4.7 Week 13 — Contract created & awarded	13

4.8 Week 14 — Handover	13

4.9 Months 1–3 — Project Execution	13

4.10 Month 2 — First invoice paid	14

4.11 Months 3–7 — Site execution	14

4.12 Month 7 — Commissioning	14

4.13 Month 8 onwards — O&M	14

5. Quick Reference & Tips	16

5.1 Test logins (local development only)	16

5.2 Common URLs	16

5.3 Day-to-day FAQ	16

Why can't I see contracts even though I'm the super admin?	16

Why don't I see the margin column on a proposal?	16

I clicked "Mark Ready for Handover" but got an error.	17

My handover Complete button is greyed out.	17

I want a daily summary instead of the bell pinging me.	17

I changed a field but the audit log doesn't show it.	17

How do I save the filter combination I always use?	17

5.4 Where to ask for help	17

6. Sales Pipeline Discipline (V1 — added April 2026)	17

6.1 What was added	17

6.2 Activity types	18

6.3 Next-action types	18

6.4 Health states	18

6.5 Daily workflow for sales	18

6.6 How to log an activity	18

6.7 Setting and updating the next action	19

6.8 Sales Pipeline dashboard sections	19

6.9 New notifications wired in this release	19

6.10 New permissions	19

6.11 Worked example — proposal goes quiet	19

6.12 Do's and don'ts	20

6.13 Related artefacts	20

# 1. System Architecture

Solaroo RE CRM is a modular monolith — one codebase, one deployment, multiple internal modules. It is NOT a SaaS product. Everyone in the company shares the same instance.

## 1.1 Technology Stack

| Frontend | Next.js 14 (App Router), React 18, TypeScript, Tailwind CSS |
| --- | --- |
| Backend API | NestJS 10 with Fastify; TypeScript end-to-end |
| Database | PostgreSQL 16 via Prisma ORM (multi-file schema) |
| Worker | Standalone Node process (services/worker) — runs daily digest + future cron jobs |
| Auth | JWT in httpOnly cookie + role + permission engine |
| Infra | Local: pnpm dev. Production: Railway (Hobby plan) — Web, API, PostgreSQL |

## 1.2 Module Map

The codebase is organised into focused domain modules. Each owns its API routes, service logic, validation schemas, and any workflow rules.

- Auth & Admin — login, user management, role administration, permissions

- Accounts & Contacts — customer organisations and the people inside them

- Sites — physical locations where projects are delivered

- Opportunities — sales pipeline (LEAD → QUALIFIED → PROPOSAL → NEGOTIATION → WON/LOST)

- Proposals — versioned commercial offers with frozen assumption sets

- Contracts — awarded commercial agreements + handover workflow + milestones + invoices

- Projects — execution workspace for won work; gates, deliverables, members, blockers

- Documents — versioned files with approval workflow, linkable to any context

- Procurement — vendors, RFQs, purchase orders, deliveries

- Notifications — in-app bell + daily digest worker

- Reporting & PMO — dashboards, governance views, audit log

- O&M — assets, maintenance plans, service tickets, warranty tracking

## 1.3 Information Flow

A single project moves through these stages, gaining records as it goes:

Account → Site → Opportunity → Proposal → Contract → Project → Gates 1–6 → Commissioning → Asset Register → O&M

Each transition leaves an audit trail (who, when, what changed) and may fire one or more notifications.

## 1.4 Permission Model

Three layers protect data:

- Role-based — every user has exactly one role (e.g. PROJECT_MANAGER). Roles map to a set of permissions.

- Scope-based — most permissions carry a scope: own / assigned / team / all. Example: PROJECT_ENGINEER has project:view at "assigned" scope, meaning they only see projects they are a member of.

- Field-level — sensitive fields (margin, contract value, cost) are stripped server-side from responses for users without view_value or view_estimated permissions.

Default posture is restrictive. New roles see less, not more. Audit log captures every state transition.

# 2. Roles & Responsibilities

Solaroo CRM ships with 14 roles covering the full project lifecycle. The table below lists each role, who it represents, and what they own day-to-day.

| Role | Who they are | What they own in the CRM |
| --- | --- | --- |
| DIRECTOR | Company leadership / management | Full visibility, all approvals, dashboards, margin & cost figures, contract sign-off, gate approvals |
| PMO_MANAGER | Head of project delivery governance | PMO dashboard, project gate approvals, contract handover, audit log oversight, cross-project blocker triage |
| SALES_MANAGER | Head of sales | Team-wide opportunity & proposal visibility, contract creation/edit, margin visibility, account approvals |
| SALES_ENGINEER | Front-line sales / business development | Owns accounts, opportunities, site assessments, proposal drafting; sees own pipeline only |
| PROJECT_MANAGER | PM running one or more delivery projects | Project edit, member management, gate submission/approval, blocker handoff, view assigned contracts |
| PROJECT_ENGINEER | PM's engineer working on the same project | Project edit (limited), gate work, deliverable status, view assigned proposals & contracts |
| DESIGN_LEAD | Head of engineering / design dept | Design Basis approvals, drawings, technical reviews, design team assignments |
| DESIGN_ENGINEER | Drafter / designer | Drawings, design submittals, technical assessment work, view assigned opportunities |
| PROCUREMENT | Buyer / supply chain | Vendors, RFQs, purchase orders, deliveries; sees POs assigned to their projects |
| SITE_SUPERVISOR | On-site execution lead | Site logs, punch lists, daily progress, photos; mobile-first usage |
| COMMISSIONING_ENGINEER | Testing & handover specialist | Commissioning tests, asset registration, handover docs |
| OM_ENGINEER | Operations & maintenance engineer | Asset history, service tickets, maintenance plans, warranty claims |
| FINANCE_ADMIN | Finance / accounts admin | Contracts, invoice milestones, payment status, budget visibility |
| SUPER_ADMIN | IT / system administrator | User management, role administration, audit log oversight; NOT business data |

Important: SUPER_ADMIN is intentionally not a business role. They cannot see contracts, projects, or commercial data. To exercise the CRM as a real user, log in as a DIRECTOR or PMO_MANAGER test account.

# 3. Workflows

Each business workflow below maps to a distinct module in the CRM. They are presented in lifecycle order — the order a single piece of work flows through the system.

## 3.1 Lead → Opportunity

A SALES_ENGINEER captures every customer conversation as an Opportunity, attached to an Account and a Site. The opportunity moves through five stages:

| Stage | What it means | Who normally moves it forward |
| --- | --- | --- |
| LEAD | Initial conversation logged. Site identified. | SALES_ENGINEER |
| QUALIFIED | Customer has confirmed interest, budget, timeline. | SALES_ENGINEER |
| PROPOSAL | A formal proposal version has been issued. | SALES_ENGINEER → SALES_MANAGER |
| NEGOTIATION | Customer reviewing; commercial back-and-forth. | SALES_ENGINEER + SALES_MANAGER |
| WON / LOST | Terminal. WON auto-creates a Project record. | SALES_MANAGER + DIRECTOR |

Every transition is captured in the audit log. WON requires a project code and a Project Manager; LOST requires a written reason. Both fire targeted notifications: WON → DIRECTOR, SALES_MANAGER, the new PM. LOST → opportunity owner, SALES_MANAGER, DIRECTOR.

## 3.2 Proposal

A Proposal is the formal commercial document. It can have multiple versions; once a version is APPROVED, it becomes immutable — any change requires a new version.

- Each version carries: title, technical & commercial summaries, estimated CAPEX, estimated margin %, estimated annual savings, payback years.

- Margin and CAPEX are gated on the contract:view_value / margin:view_estimated permissions — execution roles see "—" instead of the figure.

- Approval workflow: DRAFT → SUBMITTED → UNDER_REVIEW → APPROVED / REJECTED / RETURNED.

- SALES_ENGINEER drafts. SALES_MANAGER or DIRECTOR approves.

- Each approved version freezes its assumption set (escalation rates, FX, contingency %) — recoverable evidence trail.

## 3.3 Contract & Award→Handover

When a customer signs, the team creates a Contract record. The Contract is the commercial spine — it carries the contracted value, payment terms, milestones, invoices, and the signed PDF.

Contract status moves through:

DRAFT → UNDER_REVIEW → AWARDED → SIGNED → ACTIVE → CLOSED

In parallel, a separate Handover sub-workflow tracks the bridge from commercial commitment to delivery kickoff:

NOT_STARTED → READY → IN_PROGRESS → COMPLETED

Both axes compose. A contract can be AWARDED + IN_PROGRESS handover at the same time. The handover workflow is gated:

- To mark READY: contract must be AWARDED, with site, opportunity, PM candidate, awarded date, target COD, and contract value > 0.

- To begin handover: status must be READY.

- To complete: every checklist item must be ticked AND the contract must have a linked opportunity, site, and PM (override allowed at this step).

Default 6-item handover checklist: signed contract uploaded · site visit confirmed · DBD accepted · long-lead procurement identified · PM assigned · kickoff scheduled.

On COMPLETED, the system either creates a new Project from the contract context OR links to the project already created at WON time. Contract status auto-promotes to ACTIVE.

## 3.4 Milestones & Invoices

Each contract decomposes into one or more invoice milestones (e.g. "30% on signing", "60% on delivery", "10% on commissioning"). Each milestone can be linked to one Invoice.

- Milestones: created by DIRECTOR / FINANCE_ADMIN / SALES_MANAGER. Toggle "Mark achieved" when the trigger condition is met (auto-stamps achievedDate).

- Invoices: created by FINANCE_ADMIN / DIRECTOR. Linked to a milestone via dropdown (the milestone's invoiceId is set as a side-effect, so each milestone has at most one invoice).

- Invoice status: NOT_RAISED → RAISED → SUBMITTED → PARTIALLY_PAID → PAID (or DISPUTED). Status update is a one-click dropdown change.

- On PAID transition: notification fires to DIRECTOR + FINANCE_ADMIN + project PM.

## 3.5 Project Execution — Gates 1 to 6

Every project is structured around 6 phase gates. Each gate has a checklist of deliverables. The project cannot advance past a gate until that gate is APPROVED by an authorised reviewer.

| Gate | Name | Typical content |
| --- | --- | --- |
| G1 | Contract & Project Handover | Signed contract pack, baseline budget, PM appointment, kickoff minutes |
| G2 | Design Freeze | Design Basis Document, single-line diagram, layout drawings, BoQ |
| G3 | Procurement Release | PO release, vendor confirmations, long-lead delivery confirmations |
| G4 | Site Execution | Daily site logs, milestone photos, QA records, RFI log |
| G5 | Commissioning | Test sheets, performance reports, customer acceptance |
| G6 | Financial Close-out | As-built drawings, asset register, handover pack, defect liability start |

Each gate moves through: NOT_STARTED → IN_PROGRESS → SUBMITTED → APPROVED (or REJECTED → re-open). Submission is by the PM. Approval is by DIRECTOR / PMO_MANAGER (or PROJECT_MANAGER for assigned-scope gates per role config).

Per-gate audit trail is rendered inside the expanded gate panel — every status change, deliverable approval, and PMO comment is captured.

## 3.6 Documents & Revisions

Any record (Opportunity, Project, Contract) can have files attached. Each file is a Document with one or more Revisions.

- Upload via the Documents panel on the relevant detail page. Files go under uploads/{type}/{id}/{category}/.

- Each revision has approvalStatus: PENDING → APPROVED / REJECTED. DESIGN_LEAD or DIRECTOR approves; PROJECT_MANAGER can approve assigned-scope.

- Approve / Reject buttons appear on PENDING revisions in the revision history dialog.

- Reject requires a written reason. The uploader is notified.

## 3.7 Procurement

- PROCUREMENT users create Vendors, then Purchase Orders, optionally linked to a Project.

- PO status: DRAFT → ISSUED → ACKNOWLEDGED → PARTIAL_DELIVERY → DELIVERED → CLOSED.

- Status changes notify project PM + project members + all PROCUREMENT-role users (so the rest of the supply chain stays in the loop).

- Deliveries are tracked under each PO with received-quantity logging.

## 3.8 Commissioning & O&M

At G5 the COMMISSIONING_ENGINEER records test sheets and registers each installed asset (PV string, inverter, battery rack, BMS, etc) with serial number and warranty start date. After G6, ownership shifts to OM_ENGINEER:

- OM_ENGINEER maintains the asset register, logs service tickets, and tracks warranty claims.

- Maintenance plans (annual visits, quarterly checks) are scheduled per asset.

- Site team logs daily readings; deviations beyond threshold raise a service ticket.

## 3.9 PMO Dashboard

The /pmo route is the single command centre for PMO_MANAGER and DIRECTOR. It shows:

- Quick-count tiles: total active projects, RED projects, blockers, pending gate approvals, overdue deliverables, overdue milestones, critical issues, pending proposal approvals.

- Gate distribution histogram (active projects per gate 1–6).

- Projects with active blockers — sorted by RAG status and blocker due date.

- Pending gate approvals — submitted gates waiting for sign-off.

- Stalled projects — no update in the last 14 days.

- Commercial cash position — contracted vs invoiced vs paid, per currency, with a stacked bar.

- Recent activity — last 15 audit-log events across all modules.

## 3.10 Notifications & Daily Digest

The bell icon in the top bar polls every 30 seconds for unread notifications. Click to see the last 50; "View all" opens a paginated /notifications page that includes dismissed items.

Notification triggers (current set):

- Opportunity stage changes — WON / LOST notify the right leadership; intermediate stages notify the owner.

- Gate transitions — SUBMITTED notifies approvers; APPROVED / REJECTED notify PM + project members.

- Deliverable APPROVED — PM + project members.

- Blocker assignment — the new owner is notified directly.

- Project member added — the new member + the PM.

- Document APPROVED / REJECTED — uploader + document owner + project PM.

- PO status changes — project PM + members + all PROCUREMENT users.

- Contract awarded / handover ready / handover completed — relevant leadership + the PM candidate.

- Invoice PAID — FINANCE_ADMIN + DIRECTOR + project PM.

Each user can opt into a daily digest from the /notifications page header. When enabled, a worker process summarises any unread notifications from the last 24 hours into a single in-app digest message — useful for users who want to silence the bell during deep work.

## 3.11 Saved Views

Above the filter row on list pages, a Saved Views bar lets each user save the current filter combination under a name (e.g. "My active commercial work"). One view per module can be marked Default — it auto-applies on page load. Implemented today on the /contracts list; same component drops into other list pages without backend changes.

## 3.12 Audit Log

Every state-changing action records to the global audit log. The log can be browsed two ways:

- Per record: each detail page (Contract, Gate panel) shows a compact trail of just that record's history.

- Globally: /admin/audit lets DIRECTOR / PMO_MANAGER / SUPER_ADMIN filter by resource type, record ID, user, or date range.

Recorded fields: actor, resource, resourceId, action, optional field-name + old/new value, free-form metadata. Failures during audit recording are swallowed so they never break the main transaction.

# 4. Worked Example — One Project, End-to-End

This section follows ONE realistic project through the system. Use it as a script when training new users — every action below maps to a specific page and button in the live CRM.

Example project: "Pulau Tioman Resort — 2 MWp PV + 4 MWh BESS Hybrid"  Customer: Tioman Beach Resort Sdn Bhd · Site: Pulau Tioman, Pahang (off-grid island, currently runs on diesel) · Commercial model: Build-Own-Operate over 15 years.

## 4.1 Day 1 — Sales Engineer captures the lead

Aisha (SALES_ENGINEER) returns from a customer site visit. She:

- Opens /accounts → New Account → "Tioman Beach Resort Sdn Bhd" with primary contact "Encik Razak (Operations Manager)".

- Opens /sites → New Site → "Tioman Resort Main Compound", grid category OFF_GRID_DIESEL, 2.4 MW peak demand.

- Opens /opportunities → New → title "Tioman 2 MWp Hybrid PV+BESS", account = the new resort, site = main compound, owner = Aisha, stage LEAD, estimatedValue RM 18,500,000, expectedAwardDate 2026-08-15.

- Logs first activity: "Customer keen, currently spending RM 1.6 M / year on diesel. Meeting with CFO in 2 weeks."

## 4.2 Week 2 — Qualification

After the CFO meeting, Aisha advances the stage:

- Opens the opportunity → "Move stage" → QUALIFIED. Adds reason "Budget confirmed; technical scoping next."

- Audit log entry: opp_stage_changed (Aisha · LEAD → QUALIFIED).

- No notification (intermediate stage moves only notify the owner — Aisha is the owner).

## 4.3 Week 4 — Technical Assessment

Aisha books the engineering team. Daniel (DESIGN_ENGINEER) is added as an Opportunity Member so he can see the record.

- Daniel uploads load profile + irradiance data via /opportunities/<id>/documents.

- Aisha logs the site visit notes under Activities.

- Vivian (DESIGN_LEAD) reviews the technical assessment and approves it.

## 4.4 Week 6 — Proposal v1 issued

- Aisha clicks "New Proposal" from the opportunity. Title = "Tioman Hybrid v1.0".

- Drafts a Proposal Version 1 with technical summary, commercial summary, estimated CAPEX RM 16.2 M, estimated margin RM 2.3 M (14%), payback 4.1 years.

- Submits the version for approval. Khairul (SALES_MANAGER) is notified.

- Khairul approves. The version is now immutable; the assumption set is frozen.

- Stage moves to PROPOSAL.

## 4.5 Week 9 — Negotiation

- Customer requests change in payment terms. Aisha drafts Proposal Version 2 with revised commercials.

- Stage manually moved to NEGOTIATION.

- After two more rounds, customer accepts v2.

## 4.6 Week 12 — WON

Aisha clicks "Move stage" → WON. The dialog requires:

- projectCode: "SRE26-TBR001"

- projectName: "Tioman Hybrid PV+BESS"

- projectManagerId: Lim Wei Jian (PROJECT_MANAGER)

- budgetBaseline: RM 16,200,000

- startDate: 2026-09-01 · targetCod: 2027-04-30

Result:

- Project SRE26-TBR001 is auto-created with Lim Wei Jian as PM, gates 1–6 pre-populated with deliverable templates.

- Notifications fire: Lim (the new PM), DIRECTOR, all SALES_MANAGER users.

- Audit row: opp_stage_changed (Aisha · NEGOTIATION → WON · projectCreated = SRE26-TBR001).

## 4.7 Week 13 — Contract created & awarded

Khairul (SALES_MANAGER) creates the Contract record:

- /contracts/new → contractNo "TBR-2026-001", title "Tioman Hybrid Build-Own-Operate", account = Tioman Resort, opportunity = the won opp, site = main compound, projectManagerCandidateId = Lim Wei Jian, contractValue RM 16,200,000, awardedDate 2026-08-22, targetCod 2027-04-30.

- Khairul opens the new contract → clicks "Mark as Awarded". Contract status = AWARDED. Notifications fire to DIRECTOR + PMO_MANAGER + FINANCE_ADMIN + Lim. Audit row: contract status_changed (DRAFT → AWARDED).

- Khairul scrolls down → "Add milestone" three times: M1 30% on signing (RM 4.86 M, target 2026-09-01), M2 60% on equipment delivery (RM 9.72 M, target 2027-02-28), M3 10% on commissioning (RM 1.62 M, target 2027-04-30).

- Customer signs. Khairul uploads the signed PDF in the Documents panel of the contract — it lands at uploads/contracts/<id>/contracts/.

## 4.8 Week 14 — Handover

Hafiz (PMO_MANAGER) opens the contract:

- Clicks "Mark Ready for Handover". The system checks all required fields are present; the default 6-item handover checklist appears. Notifications fire to PMO + DIRECTOR + Lim.

- Clicks "Begin Handover". State = IN_PROGRESS.

- Over the next week, Hafiz ticks each checklist item as it gets done. Each tick is captured (completedAt + completedById).

- All 6 ticked. Hafiz clicks "Complete Handover & Activate Project". The picker offers to override PM (he keeps Lim Wei Jian). Confirmed.

- Result: contract handoverStatus = COMPLETED, status = ACTIVE, project SRE26-TBR001 gets contractId set on it (now visible as a "Contract: TBR-2026-001" badge on the project header). Notifications fire to leadership.

## 4.9 Months 1–3 — Project Execution

- Lim opens /projects/SRE26-TBR001. Adds Daniel and Wei Han as project members via "Add member".

- Gate 1 deliverables: Lim ticks "Contract Pack" (uploaded earlier), "Baseline Budget" (uses the RM 16.2 M from the contract).

- Lim submits Gate 1. Hafiz (PMO_MANAGER) approves it. Audit + notification fire. Project currentGateNo advances to 2.

- Gate 2 (Design Freeze): Daniel uploads the DBD revision A. Vivian approves. Lim submits Gate 2. Hafiz approves.

- Gate 3 (Procurement Release): Aiman (PROCUREMENT) creates POs against approved vendors. Each PO is linked to project SRE26-TBR001.

## 4.10 Month 2 — First invoice paid

- Khairul opens the contract → Milestones panel → ticks "Mark achieved" on M1 (signing milestone).

- Khairul switches to Invoices panel → "Add invoice" → invoiceNo INV-2026-0042, milestone = M1, amount RM 4,860,000 (sets totalAmount), invoiceDate today, dueDate +30 days.

- A week later: customer pays. Khairul changes invoice status from RAISED → PAID via the dropdown. paidDate auto-stamps. paidAmount auto-fills as RM 4,860,000.

- Notification fires: "Invoice paid: INV-2026-0042 — TBR-2026-001 · Tioman Hybrid Build-Own-Operate · MYR 4,860,000.00 received." → DIRECTOR + FINANCE_ADMIN + Lim.

- Cash-position panel on the contract now shows: Contracted MYR 16,200,000 · Invoiced MYR 4,860,000 (30%) · Paid MYR 4,860,000 (30%) · Outstanding MYR 11,340,000.

- Same numbers roll up to the PMO dashboard "Commercial cash position" widget.

## 4.11 Months 3–7 — Site execution

- Daud (SITE_SUPERVISOR) records daily site logs via mobile.

- Long-lead inverter from Sungrow is delayed by 3 weeks. Lim raises a blocker on the project: "Inverter delivery delayed — recovery plan to compress commissioning window." Assigns blockerOwner = Aiman (PROCUREMENT), blockerDueDate = 2027-03-15, ragStatus = AMBER.

- Aiman gets a notification: "You've been assigned a blocker on SRE26-TBR001…" Audit row: blocker_owner_assigned.

- Gate 4 (Site Execution) deliverables ticked off as work progresses. Photos uploaded. Punch list maintained.

## 4.12 Month 7 — Commissioning

- Faridah (COMMISSIONING_ENGINEER) records test sheets, registers each PV string + inverter + BESS rack with serial numbers, warranty start dates.

- Customer issues acceptance certificate. Lim submits Gate 5. Hafiz approves.

- Khairul marks M3 (commissioning milestone) as achieved → adds the final invoice → marks PAID after customer settlement.

- Final cash position: Contracted RM 16.2 M · Paid RM 16.2 M · Outstanding RM 0.

## 4.13 Month 8 onwards — O&M

- Project transitions to O&M ownership. The OM_ENGINEER (Tan) inherits the asset register from commissioning.

- Quarterly maintenance plan auto-schedules: site visits in months 11, 14, 17, 20.

- When an inverter fault triggers a service ticket, the warranty record is consulted automatically to determine if the fix is in-warranty.

# 5. Quick Reference & Tips

## 5.1 Test logins (local development only)

All test users use password Test@1234. The super-admin uses Solaroo123!.

| Super admin (system only) | see@pekatgroup.com |
| --- | --- |
| Director | director@pekatgroup.com |
| PMO Manager | pmo@pekatgroup.com |
| Sales Manager | salesmanager@pekatgroup.com |
| Sales Engineer | sales1@pekatgroup.com |
| Project Manager | pm1@pekatgroup.com |
| Project Engineer | pe1@pekatgroup.com |
| Design Lead | designlead@pekatgroup.com |
| Design Engineer | designer1@pekatgroup.com |
| Procurement | procurement@pekatgroup.com |
| Site Supervisor | site1@pekatgroup.com |
| Commissioning Engineer | commissioning@pekatgroup.com |
| O&M Engineer | om1@pekatgroup.com |
| Finance / Admin | finance@pekatgroup.com |

## 5.2 Common URLs

| Local web | http://localhost:3000 |
| --- | --- |
| Local API | http://localhost:4000/api |
| Notifications page | /notifications |
| Audit log (admin) | /admin/audit |
| User management | /admin/users (SUPER_ADMIN only) |
| PMO dashboard | /pmo |
| Contracts list | /contracts |

## 5.3 Day-to-day FAQ

### Why can't I see contracts even though I'm the super admin?

SUPER_ADMIN intentionally has no commercial-data permissions. Switch to a DIRECTOR or PMO_MANAGER test account.

### Why don't I see the margin column on a proposal?

Margin and CAPEX are gated on the margin:view_estimated permission, granted to DIRECTOR / SALES_MANAGER / SALES_ENGINEER (own scope) / FINANCE_ADMIN. Other roles see "—".

### I clicked "Mark Ready for Handover" but got an error.

The contract is missing one of the required fields. The error message lists which one. Edit the contract to fill it in, then retry.

### My handover Complete button is greyed out.

At least one checklist item is still unticked. Tick all items in the handover panel first.

### I want a daily summary instead of the bell pinging me.

Open /notifications → click the "Daily digest: OFF" button in the top right to flip it to ON. The worker creates a single in-app digest notification once per 24 hours summarising what you missed.

### I changed a field but the audit log doesn't show it.

Only state transitions and key approvals are audited (gate status, deliverable status, contract status, blocker owner, member add/remove, document approve/reject, etc). Free-form field edits to text/number fields are not currently captured.

### How do I save the filter combination I always use?

On the contracts list page, the Saved Views bar at the top lets you save the current filters under a name. Tick "Default" to have it auto-apply when you open the page next time.

## 5.4 Where to ask for help

In order of preference:

- Search /admin/audit for a recent action that matches what you saw — the metadata often reveals the cause.

- Check the dev_log/ folder in the repo for the most recent dev_log_YYMMDD.txt — it documents architecture decisions, known limitations, and recent changes.

- Direct message see@pekatgroup.com — the project lead.

# 6. Sales Pipeline Discipline (V1 — added April 2026)

This section documents the Sales Pipeline Discipline module added in April 2026. The earlier sections describe the original lifecycle; this section adds the activity-logging, next-action, health, and dashboard layers that now sit on top of every opportunity.

## 6.1 What was added

- Activity Timeline — every call, email, WhatsApp, meeting, site visit, or proposal follow-up is logged on the opportunity (and visible from the linked account, contact, and site).

- Next-Action Tracking — every open opportunity carries one structured next action (type, owner, due date).

- Opportunity Health — a coloured pill (Healthy · At Risk · Stale · Overdue) is computed at read time on every list row and detail page.

- Sales Pipeline Dashboard — a dedicated page (sidebar → Sales Pipeline) summarising pipeline value, stage breakdown, follow-up backlog, proposal monitoring, and the closing forecast.

- 12 filter chips on the Opportunities list (My Open, Closing this month / quarter, No next action, Overdue, No activity 14d / 30d, Proposal submitted, High value, Won this month, Lost this month, Next-action status).

- 3 new in-app notifications: Overdue next action (daily), Proposal awaiting follow-up (3d silence), Stale opportunity (14d silence). All routed via the existing bell + daily digest.

## 6.2 Activity types

- CALL — phone call (inbound or outbound).

- EMAIL — email correspondence.

- WHATSAPP — WhatsApp / chat conversation.

- MEETING — meeting (in-person or virtual).

- SITE_VISIT — on-site visit, optionally linked to a Site record.

- PROPOSAL_FOLLOW_UP — specifically chasing an outstanding proposal.

- GENERAL_NOTE — internal notes that don't fit the above.

Every activity must link to at least one of: account, contact, site, or opportunity. When you log from inside one of those records, the link is auto-filled.

## 6.3 Next-action types

- FOLLOW_UP — generic follow-up call/email/message.

- SITE_SURVEY — schedule or perform a technical site survey.

- PROPOSAL_PREP — prepare or revise a proposal.

- PROPOSAL_PRESENTATION — present the proposal to the customer.

- NEGOTIATION — commercial negotiation step.

- CONTRACT — send, review, or chase the contract.

- INTERNAL_REVIEW — internal sign-off needed before next external step.

- OTHER — anything else; describe in the notes field.

## 6.4 Health states

- Healthy (green) — recent activity, next action set and not overdue.

- At Risk (amber) — either no next action set, or no activity in the last 14 days.

- Stale (orange) — no activity logged in the last 30 days.

- Overdue (red) — next action is past its due date and still PENDING.

Closed opportunities (WON or LOST) are always Healthy — the health flag only applies to live deals. Health is computed at read time, never stored.

## 6.5 Daily workflow for sales

- Open the Sales Pipeline page (sidebar → Sales Pipeline). Scan Follow-up monitoring and Closing forecast.

- Open the Opportunities list. Click the My Open chip, then the Overdue chip. Work the red rows first.

- On each opportunity, log every conversation as an activity (Subject + short body).

- After logging, update the next action: type, owner, due date. If the deal is done for now, mark complete and immediately set the next next-action.

- End of day: any Stale or At Risk row should have either a logged activity or a future next action by close of business.

## 6.6 How to log an activity

- Open the opportunity, scroll to the Activity Timeline panel.

- Click Log activity at the top right of the panel.

- Pick a type chip (CALL, EMAIL, WHATSAPP, MEETING, SITE_VISIT, PROPOSAL_FOLLOW_UP, GENERAL_NOTE).

- Enter Subject (one short line), optional Body, Occurred at (defaults to now).

- Save. Activity appears at top of timeline and updates the opportunity health and last-activity time immediately.

You can edit your own activity at any time. You can delete your own activity within 7 days of creation; after that, ask a Director. Sales Managers can edit/delete activities owned by their team.

## 6.7 Setting and updating the next action

- Click Edit on the Next Action panel on the opportunity detail page.

- Pick Type (FOLLOW_UP, SITE_SURVEY, etc.).

- Pick Owner (defaults to you; reassign if it's a colleague's step).

- Set a realistic Due Date — the system flags it OVERDUE the moment the date passes.

- Optional notes. Save.

When you complete an action: open the panel → Mark complete → set the next one. An open opportunity should never be left without a next action — that triggers the At Risk flag.

## 6.8 Sales Pipeline dashboard sections

- Pipeline summary — open count, total weighted value, average deal size.

- By stage — count and value per stage; spot where the pipeline is bunching.

- Sales activity — activities logged this week vs last week, by type.

- Follow-up monitoring — opportunities with overdue next actions, broken out by owner.

- Proposal monitoring — proposals submitted with no follow-up activity in 3+ days.

- Closing forecast — what is forecast to close this month / quarter, weighted.

- Top 10 — the 10 highest-value open opportunities.

- Won this month — recent closed business summary.

Visibility: Sales Engineers see their own pipeline; Sales Managers see the team's; Directors see everything.

## 6.9 New notifications wired in this release

- next_action_overdue — fired once per day (worker tick = hourly, deduped within 22h) until the action is completed or rescheduled. Routes to the action owner and the opportunity owner.

- proposal_no_followup — fired when a BUDGETARY_PROPOSAL or FIRM_PROPOSAL stage opportunity has no logged activity for 3 days. Routes to the opportunity owner.

- opportunity_stale — fired when any open opportunity has no logged activity for 14 days. Routes to the opportunity owner.

All three respect the existing daily-digest opt-in (User → notificationDigestEnabled). Dedupe is enforced via the Notification table itself — no new schema field was added.

## 6.10 New permissions

- activity:create:own — Sales Engineer.

- activity:edit:own / activity:delete:own — owner of the activity (7-day delete window for non-Director).

- activity:view:assigned — PM, Project Engineer, Design Engineer (see activities on their assigned opps/projects).

- activity:view:team / edit:team / delete:team — Sales Manager.

- activity:view:all / edit:all / delete:all — Director, PMO Manager, Finance Admin.

## 6.11 Worked example — proposal goes quiet

- After issuing a proposal, set the next action: FOLLOW_UP, due in 3 working days.

- On the due date, call or message the customer.

- Log the contact attempt as PROPOSAL_FOLLOW_UP regardless of whether they answered.

- Reset the next action with a new due date — never leave it empty.

- If 3 days pass with no logged activity, the system fires proposal_no_followup to your bell.

- If 14 days pass with no activity, the system fires opportunity_stale and the row turns Stale on every list.

## 6.12 Do's and don'ts

- DO log activities the same day they happen — your timeline is the audit trail.

- DO keep one and only one open next action per live opportunity.

- DO use Saved Views to keep your daily working set small.

- DO NOT delete activities to clean up the timeline — the 7-day delete window is for genuine mistakes.

- DO NOT skip the next-action update after logging an activity — that is the most common cause of At Risk flags.

- DO NOT use GENERAL_NOTE for everything — picking the right activity type is what powers the dashboard charts.

## 6.13 Related artefacts

- Solaroo_Sales_Pipeline_Onboarding.docx — standalone sales-onboarding guide (same material, narrower scope, designed for new-hire reading).

- Solaroo_CRM_Flowcharts.pptx — 10-slide visual deck of the full sales-to-project lifecycle, including swim-lane and stage-flow diagrams.

- dev_log/dev_log_260427.txt — implementation log for this module (schema diffs, new endpoints, test checklist).